## Sheet1
Priority |  | Est Effort (hours) | Act Effort
1 | Display message to registered users who have not yet paid | 4
1 | Auto-pick team at deadline | 6
1 | Competition Standings | 4
1 | Include information on charity | 2
1 | Splash screen for first time users summerising competition rules | 5
1 | Payment page | 5
1 | Refactor headers and footers | 1 | 1
1 | Refactor DAL - include disconnects, monitor performance | 3
1 | Add "Full name" field to registration a | 1
2 | Where a user is eliminated, indicate this at login, show history | 4
2 | Player History | 4
2 | Header tabs to select "Home¦User Settings ¦ league" | 2
2 | Fix footer - change to navbar | 2
2 | Fix "History for... " injection of username | 1 |  | in progress
3 | Disable teams that user cannot select | 2 |  | Done
3 | Image background | 3
3 | Style text content blocks correctly | 3
3 | Style confirmation dialogs (avoid browser native) | 2
3 | Show team/match selection in confirm dialog before submitting prediction | 1
3 | Fix header navbar (white highlight on middle 2 buttons) | 2
57