## Sheet1
|  | Est Effort (hours) | Act Effort
1 | Display message to registered users who have not yet paid | 4
2 | Where a user is eliminated, indicate this at login, show history | 4
3 | Disable teams that user cannot select | 2
4 | Image background | 3
5 | Style text content blocks correctly | 3
6 | Auto-pick team at deadline | 6
7 | Competition Standings | 4
8 | Player History | 4
9 | Style confirmation dialogs (avoid browser native) | 2
10 | Show team/match selection in confirm dialog before submitting prediction | 1
11 | Header tabs to select "Home¦User Settings ¦ league" | 2
12 | Include information on charity | 2
13 | Splash screen for first time users summerising competition rules | 5
14 | Payment page | 5 |  | in progress
15 | Refactor headers and footers | 1 | 1 | Done
16 | Refactor DAL - include disconnects, monitor performance | 3
51